## Start Here
Wedding Day Checklist
Your hour-by-hour guide from the night before to the morning after, with a pack list, helper roles and vendor payments in one file.
Wedding date (type yours) |  |  | Ceremony start time |  |  | Days to go |  | Checklist ready
2027-10-09 |  |  | 16:00 |  |  | 360 |  | 0%
Tasks done |  |  | Items packed |  |  | Roles confirmed |  | Vendors confirmed
0 of 52 |  |  | 0 of 54 |  |  | 0 of 14 |  | 0 of 15
Balances due day-of |  |  | Tips planned |  |  | Vendor meals needed |  | High-priority tasks open
0 |  |  | 0 |  |  | 0 |  | 29
⚠ 14 helper role(s) not confirmed yet. Open the Who is Doing What tab. | [9 empty] | 14
15
Day-of Checklist → |  | Pack List → |  | Who's Doing What → |  | Vendors & Payments → | Emergency Contacts → |  | Tip: print the first two tabs.
WHAT'S NEXT (the next 8 tasks you haven't ticked off)
Time | Day | Task |  |  |  |  | Who |  | Where
46668.5417 | Day before | Attend the ceremony rehearsal and walk through the processional |  |  |  |  | Both |  | Ceremony site |  | 46668.5417 | 2
46668.6667 | Day before | Drop off decor, signage and personal items with the venue or your coordinator |  |  |  |  | Planner / Coordinator |  | Venue |  | 46668.6667 | 3
46668.7917 | Day before | Enjoy the rehearsal dinner; share toasts and any wedding party gifts |  |  |  |  | Both |  | Rehearsal dinner |  | 46668.7917 | 4
46668.875 | Day before | Lay out attire, rings, shoes, jewelry and accessories |  |  |  |  | Both |  | Hotel / home |  | 46668.875 | 5
46668.8958 | Day before | Give vendor payment and tip envelopes to the person handling them |  |  |  |  | Both |  | Hotel / home |  | 46668.8958 | 6
46668.9167 | Day before | Charge phones, camera batteries and power banks; set two alarms |  |  |  |  | Both |  | Hotel / home |  | 46668.9167 | 7
46668.9583 | Day before | Drink water, eat something, and get as much sleep as you can |  |  |  |  | Both |  | Hotel / home |  | 46668.9583 | 8
46669.2917 | Wedding day | Wake up, hydrate and eat a real breakfast |  |  |  |  | Both |  | Hotel / home |  | 46669.2917 | 10
PROGRESS BY PHASE
Phase |  |  | Done | Total | % complete
The Night Before |  |  | 0 | 7 | 0%
Morning |  |  | 0 | 5 | 0%
Getting Ready |  |  | 0 | 10 | 0%
Before the Ceremony |  |  | 0 | 6 | 0%
Ceremony |  |  | 0 | 4 | 0%
Cocktail Hour |  |  | 0 | 4 | 0%
Reception |  |  | 0 | 9 | 0%
Send-Off & Wrap-Up |  |  | 0 | 5 | 0%
The Morning After |  |  | 0 | 2 | 0%
HOW TO USE THIS CHECKLIST
1. Enter your wedding date and ceremony start time in the yellow cards. Every task gets a clock time. The sample date is only an example.
2. Open the Day-of Checklist. Adjust the minutes in column D to fit your schedule, set who's handling each task, then tick things off with ☐ / ☑.
3. Use the Pack List the week before. Choose who packs each item and where it goes, so nothing gets left behind.
4. Fill in Who's Doing What and confirm each person, then send them the timeline. Add vendor arrival times, balances and tips on Vendors & Payments.
5. Fill in Emergency Contacts, including your weather backup deadline. Print the Day-of Checklist, the Pack List and the contact page.
6. On the wedding day, open the file or your printout. Tasks that run late turn red, and the next task you haven't ticked is highlighted in orange.
Created by Butterfly Soiree ¦ butterflysoiree.com ¦ Full-service, luxury, day-of and destination wedding planning in San Diego, California
Formulas:
Days to go = IF([Wedding date (type yours)]="","Set date",MAX(0,[Wedding date (type yours)]-TODAY()))

## Day-of Checklist
Wedding Day Checklist
← Back to Start Here
| Wedding date: | 2027-10-09 |  | Times calculate from your ceremony start. Edit the minutes in column D to shift any task. On the wedding day, tasks that are past due turn red.
Done | Time | Day | Min. from ceremony | Task | Who's handling it | Where | Priority | Tips & notes
THE NIGHT BEFORE ¦ Rehearsal and rest
☐ | 46668.5417 | Day before | -1620 | Attend the ceremony rehearsal and walk through the processional | Both | Ceremony site | High | Confirm where everyone stands and who cues the music. | 46668.5417
☐ | 46668.6667 | Day before | -1440 | Drop off decor, signage and personal items with the venue or your coordinator | Planner / Coordinator | Venue | High | Label every box. Hand off to a coordinator, not a guest. | 46668.6667
☐ | 46668.7917 | Day before | -1260 | Enjoy the rehearsal dinner; share toasts and any wedding party gifts | Both | Rehearsal dinner | Medium |  | 46668.7917
☐ | 46668.875 | Day before | -1140 | Lay out attire, rings, shoes, jewelry and accessories | Both | Hotel / home | High | Steam or press everything tonight. | 46668.875
☐ | 46668.8958 | Day before | -1110 | Give vendor payment and tip envelopes to the person handling them | Both | Hotel / home | High | Check the Vendors & Payments tab first. | 46668.8958
☐ | 46668.9167 | Day before | -1080 | Charge phones, camera batteries and power banks; set two alarms | Both | Hotel / home | Medium |  | 46668.9167
☐ | 46668.9583 | Day before | -1020 | Drink water, eat something, and get as much sleep as you can | Both | Hotel / home | Medium |  | 46668.9583
MORNING ¦ Slow start, steady day
☐ | 46669.2917 | Wedding day | -540 | Wake up, hydrate and eat a real breakfast | Both | Hotel / home | High | Protein and water. Skip the extra coffee. | 46669.2917
☐ | 46669.3125 | Wedding day | -510 | Check the forecast; confirm backup-plan decision time with your coordinator | Planner / Coordinator | Anywhere | High | See the Emergency Contacts tab for your decision deadline. | 46669.3125
☐ | 46669.3333 | Wedding day | -480 | Share the final timeline and contact sheet with the wedding party and family | Wedding Party | Anywhere | Medium |  | 46669.3333
☐ | 46669.375 | Wedding day | -420 | Florals, rentals, lighting and decor begin arriving at the venue | Planner / Coordinator | Venue | High | Check the arrival times on the Vendors & Payments tab. | 46669.375
☐ | 46669.3958 | Wedding day | -390 | Pick up bouquets and boutonnieres if not being delivered | Wedding Party | Florist / Venue | Medium |  | 46669.3958
GETTING READY ¦ Hair, makeup, photos
☐ | 46669.4167 | Wedding day | -360 | Hair and makeup begin (first person in the chair) | Hair & makeup team | Getting-ready suite | High |  | 46669.4167
☐ | 46669.4271 | Wedding day | -345 | Eat a light lunch or snack and keep water nearby | Both | Getting-ready suite | High |  | 46669.4271
☐ | 46669.4583 | Wedding day | -300 | Photographer arrives. Hand over rings, invitations, shoes and details | Photographer | Getting-ready suite | Medium |  | 46669.4583
☐ | 46669.4792 | Wedding day | -270 | Give vendor payment and tip envelopes to your coordinator or designated person | Planner / Coordinator | Venue | High | Do this before the ceremony so you're not thinking about it later. | 46669.4792
☐ | 46669.5 | Wedding day | -240 | Final venue walkthrough: decor, signage, sound check and seating | Planner / Coordinator | Venue | High |  | 46669.5
☐ | 46669.5208 | Wedding day | -210 | Get dressed; check buttons, zippers, jewelry and accessories | Both | Getting-ready suite | High |  | 46669.5208
☐ | 46669.5417 | Wedding day | -180 | Exchange letters or gifts with your partner (optional) | Both | Getting-ready suite | Low |  | 46669.5417
☐ | 46669.5521 | Wedding day | -165 | Hand the touch-up bag and emergency kit to your point person | Wedding Party | Getting-ready suite | Medium |  | 46669.5521
☐ | 46669.5625 | Wedding day | -150 | First look and couple portraits (if you're doing one) | Photographer | Venue grounds | Medium |  | 46669.5625
☐ | 46669.5972 | Wedding day | -100 | Wedding party and family portraits | Photographer | Venue grounds | Medium | Give your photographer the family-photo list in advance. | 46669.5972
BEFORE THE CEREMONY ¦ Final 60 minutes
☐ | 46669.625 | Wedding day | -60 | Ceremony site ready: programs, signs, guest book, aisle and chairs | Planner / Coordinator | Ceremony site | High |  | 46669.625
☐ | 46669.625 | Wedding day | -60 | Confirm the rings are with the right person | Wedding Party | Ceremony site | High |  | 46669.625
☐ | 46669.6354 | Wedding day | -45 | Prelude music begins; ushers start seating guests | Vendor | Ceremony site | Medium |  | 46669.6354
☐ | 46669.6458 | Wedding day | -30 | Couple stays out of sight; take a breath and have some water | Both | Getting-ready suite | Medium |  | 46669.6458
☐ | 46669.6562 | Wedding day | -15 | Wedding party lines up; officiant in position | Planner / Coordinator | Ceremony site | High |  | 46669.6563
☐ | 46669.6632 | Wedding day | -5 | Cue the processional music | Planner / Coordinator | Ceremony site | High |  | 46669.6632
CEREMONY ¦ The main event
☐ | 46669.6667 | Wedding day | 0 | Ceremony begins | Officiant | Ceremony site | High |  | 46669.6667
☐ | 46669.6771 | Wedding day | 15 | Exchange vows and rings | Both | Ceremony site | High |  | 46669.6771
☐ | 46669.6875 | Wedding day | 30 | Sign the marriage license with your officiant (and witnesses if your state requires them) | Officiant | Ceremony site | High | Give the license to the person returning it. Rules vary by state. | 46669.6875
☐ | 46669.691 | Wedding day | 35 | Recessional and receiving line (if you're having one) | Both | Ceremony site | Medium |  | 46669.691
COCKTAIL HOUR ¦ Guests mingle, couple breathes
☐ | 46669.6944 | Wedding day | 40 | Couple eats a bite and drinks water | Both | Cocktail area | High | This is the best chance you'll get all night. | 46669.6944
☐ | 46669.6979 | Wedding day | 45 | Couple portraits (golden hour if time allows) | Photographer | Venue grounds | Medium |  | 46669.6979
☐ | 46669.7083 | Wedding day | 60 | Coordinator secures gift table, cards and card box | Planner / Coordinator | Reception | High |  | 46669.7083
☐ | 46669.7292 | Wedding day | 90 | Reception room check: place cards, centerpieces, candles, sound | Planner / Coordinator | Reception | Medium |  | 46669.7292
RECEPTION ¦ Dinner, toasts, dancing
☐ | 46669.7396 | Wedding day | 105 | Guests seated; grand entrance | Vendor | Reception | High |  | 46669.7396
☐ | 46669.7465 | Wedding day | 115 | Welcome toast and blessing | Wedding Party | Reception | Medium |  | 46669.7465
☐ | 46669.7535 | Wedding day | 125 | Dinner service begins; confirm vendors are being fed | Planner / Coordinator | Reception | High | See the Vendor Meal Needed column on the Vendors & Payments tab. | 46669.7535
☐ | 46669.7639 | Wedding day | 140 | Couple eats dinner | Both | Reception | High |  | 46669.7639
☐ | 46669.7847 | Wedding day | 170 | Toasts and speeches | Wedding Party | Reception | Medium |  | 46669.7847
☐ | 46669.7986 | Wedding day | 190 | First dance and parent dances | Both | Dance floor | High |  | 46669.7986
☐ | 46669.8125 | Wedding day | 210 | Cake cutting | Both | Reception | Medium |  | 46669.8125
☐ | 46669.8229 | Wedding day | 225 | Open dancing; check in on older guests and kids | Family | Dance floor | Low |  | 46669.8229
☐ | 46669.8542 | Wedding day | 270 | Confirm late-night snack, last call and music end time with the venue | Planner / Coordinator | Reception | Medium | Many venues have strict curfews. | 46669.8542
SEND-OFF & WRAP-UP ¦ Last dance to the last box
☐ | 46669.875 | Wedding day | 300 | Last dance and send-off | Both | Venue exit | Medium |  | 46669.875
☐ | 46669.8854 | Wedding day | 315 | Collect cards, gifts, attire, personal items and the cake top | Family | Reception | High | Assign this person weeks ahead. | 46669.8854
☐ | 46669.8958 | Wedding day | 330 | Finish final vendor payments and tips | Planner / Coordinator | Venue | High |  | 46669.8958
☐ | 46669.9062 | Wedding day | 345 | Venue closeout: decor down, rentals staged, belongings loaded | Planner / Coordinator | Venue | High | Sign any venue release forms. | 46669.9063
☐ | 46669.9167 | Wedding day | 360 | Head to the hotel with overnight bag, medications and chargers | Both | Hotel | Medium |  | 46669.9167
THE MORNING AFTER ¦ Loose ends
☐ | 46670.4167 | Next day | 1080 | Confirm pickup of leftover decor and rentals | Family | Venue | Medium |  | 46670.4167
☐ | 46670.4583 | Next day | 1140 | Return or mail the marriage license per your county's instructions | Both | Anywhere | High | Return deadlines vary by state and county. | 46670.4583

## Pack List
Pack List: Bring-and-Check
← Back to Start Here | Tick items as you pack them. Choose who is packing each one and where it's going, so nothing is left at home or in the wrong car.
Packed | Item | Category | Who packs it | Goes to | Notes
DOCUMENTS & MONEY
☐ | Marriage license (original) | Documents & Money | Both | Coordinator / license keeper | Confirm who will carry it, sign it and return it.
☐ | Photo ID for both partners | Documents & Money | Both | My bag
☐ | Vendor payment and tip envelopes, labeled | Documents & Money | Both | Coordinator / license keeper | Match the Vendors & Payments tab.
☐ | Cash in small bills for surprise tips and parking | Documents & Money | Both | My bag
☐ | Printed timeline and vendor contact sheet (several copies) | Documents & Money | Planner / Coordinator | Coordinator / license keeper
☐ | Printed vows and a backup copy | Documents & Money | Both | My bag
☐ | Toast notes for anyone speaking | Documents & Money | Wedding Party | My bag
☐ | Officiant fee or thank-you envelope (if applicable) | Documents & Money | Both | Coordinator / license keeper
CEREMONY
☐ | Wedding rings and ring box or pillow | Ceremony | Wedding Party | My bag | Give them to one person and tell the whole party who it is.
☐ | Black pen for signing the license | Ceremony | Planner / Coordinator | Coordinator / license keeper | Many offices want black ink.
☐ | Ceremony programs | Ceremony | Planner / Coordinator | Venue / coordinator
☐ | Unity ceremony items (candles, sand, etc.) | Ceremony | Planner / Coordinator | Venue / coordinator
☐ | Readings and officiant script | Ceremony | Both | Venue / coordinator
☐ | Welcome sign and ceremony signage | Ceremony | Planner / Coordinator | Venue / coordinator
☐ | Guest book and pen | Ceremony | Planner / Coordinator | Venue / coordinator
GETTING DRESSED
☐ | Dress, suit or tuxedo, steamed and in a garment bag | Getting Dressed | Both | My bag
☐ | Undergarments and shapewear | Getting Dressed | Both | My bag
☐ | Shoes, plus a comfortable backup pair | Getting Dressed | Both | My bag
☐ | Veil, headpiece and jewelry | Getting Dressed | Both | My bag
☐ | Cufflinks, tie, pocket square and belt | Getting Dressed | Both | My bag
☐ | Hangers for photos | Getting Dressed | Both | My bag
☐ | Robes or matching getting-ready outfits | Getting Dressed | Wedding Party | My bag
☐ | Bouquet and boutonnieres (confirm delivery) | Getting Dressed | Wedding Party | Venue / coordinator
TOUCH-UP BAG
☐ | Lipstick or gloss | Touch-Up Bag | Wedding Party | Touch-up bag
☐ | Blotting papers and powder | Touch-Up Bag | Wedding Party | Touch-up bag
☐ | Hairspray and bobby pins | Touch-Up Bag | Wedding Party | Touch-up bag
☐ | Deodorant and breath mints | Touch-Up Bag | Wedding Party | Touch-up bag
☐ | Hairbrush or comb | Touch-Up Bag | Wedding Party | Touch-up bag
☐ | Perfume or cologne | Touch-Up Bag | Wedding Party | Touch-up bag
☐ | Tissues | Touch-Up Bag | Wedding Party | Touch-up bag
EMERGENCY KIT
☐ | Sewing kit and safety pins | Emergency Kit | Wedding Party | Emergency kit
☐ | Double-sided fashion tape | Emergency Kit | Wedding Party | Emergency kit
☐ | Stain remover pen | Emergency Kit | Wedding Party | Emergency kit
☐ | Clear nail polish (for snags) | Emergency Kit | Wedding Party | Emergency kit
☐ | Bandages and blister pads | Emergency Kit | Wedding Party | Emergency kit
☐ | Pain reliever and antacid | Emergency Kit | Wedding Party | Emergency kit
☐ | Lint roller and scissors | Emergency Kit | Wedding Party | Emergency kit
☐ | Phone charger and power bank | Emergency Kit | Wedding Party | Emergency kit
☐ | Snacks and water bottles | Emergency Kit | Wedding Party | Emergency kit
☐ | Any personal medications you take | Emergency Kit | Both | My bag | Don't leave these in the venue.
☐ | Extra contacts or glasses | Emergency Kit | Both | My bag
☐ | Umbrella, wraps or sunscreen, depending on the forecast | Emergency Kit | Wedding Party | Emergency kit
RECEPTION
☐ | Cake knife and server | Reception | Planner / Coordinator | Venue / coordinator
☐ | Toasting glasses | Reception | Planner / Coordinator | Venue / coordinator
☐ | Card box | Reception | Planner / Coordinator | Venue / coordinator
☐ | Seating chart, table numbers and place cards | Reception | Planner / Coordinator | Venue / coordinator
☐ | Personal decor, family photos and favors | Reception | Family | Venue / coordinator
☐ | Must-play and do-not-play list; name pronunciations for the DJ or emcee | Reception | Both | Venue / coordinator | Send this to the DJ before the wedding, too.
☐ | Shuttle schedule printouts | Reception | Planner / Coordinator | Venue / coordinator
OVERNIGHT & HONEYMOON
☐ | Going-away outfit | Overnight & Honeymoon | Both | Hotel
☐ | Overnight bag with toiletries | Overnight & Honeymoon | Both | Hotel
☐ | Phone and laptop chargers | Overnight & Honeymoon | Both | Hotel
☐ | Passports and travel documents (if flying soon after) | Overnight & Honeymoon | Both | Hotel
☐ | Medications and glasses case | Overnight & Honeymoon | Both | Hotel

## Who's Doing What
Who's Doing What
← Back to Start Here
Give every job a name, so no one on the wedding day has to ask who is handling it. Confirm each person, then brief them with the timeline.
Role | What they do | Person | Phone | Confirmed? | Briefed with timeline?
Day-of coordinator / main point of contact | Fields every vendor and guest question so you don't have to.
Vendor payment and tip handler | Hands out the labeled envelopes at the right time and collects receipts.
Marriage license keeper | Carries the license, makes sure it's signed, and returns it after the wedding.
Emergency kit and touch-up bag holder | Stays close to the couple with the kit, snacks and water.
Ring keeper | Holds the rings until the ceremony and hands them over at the right moment.
Gift and card table monitor | Keeps an eye on the card box and gifts, then moves them to a safe place.
Personal items and attire collector | Gathers attire, bags, gifts and the cake top at the end of the night.
Decor pack-down lead | Boxes personal decor and coordinates pickup with the venue.
Vendor meal coordinator | Makes sure each vendor who needs a meal gets one.
Transportation point person | Confirms pickups, shuttle times and parking for family and the wedding party.
Family photo wrangler | Rounds up family groups for photos using your photographer's list.
Getting-ready point person | Keeps the morning on schedule: hair, makeup, food and photos.
Out-of-town guest greeter | Welcomes guests who traveled and points them to the ceremony.
Hotel check-in / ride home | Gets the couple and the bags to the hotel at the end of the night.

## Vendors & Payments
Vendors & Day-of Payments
← Back to Start Here
Many vendor contracts already include gratuity or a service charge, so check before you add a tip. Tipping is your decision, so amounts here are yours to set.
[6 empty] | Balances due day-of | Tips planned | Envelopes ready | Vendor meals | Confirmed
[6 empty] | 0 | 0 | 0 | 0 | 0
Vendor Type | Company | Day-of Contact | Cell Phone | Arrival Time | Done By | Balance Due Day-of ($) | Tip ($) | Envelope Ready | Vendor Meal Needed | Confirmed | Notes
Photographer (EXAMPLE) | Sample Studio | Jamie Lee | (619) 555-0123 | 13:00 | 22:30 | 1500 | 200 | ☑ | Yes | Yes | Example row. Not counted in totals.
Planner / Coordinator
Photographer
Videographer
DJ / Band
Caterer
Bartender
Florist / Designer
Hair stylist
Makeup artist
Officiant
Bakery
Rentals
Lighting / AV
Transportation
Venue manager

## Emergency Contacts
Emergency Contacts & Backup Plan
← Back to Start Here
Who / what | Name | Phone | Address or notes
KEY PEOPLE
Day-of coordinator
Venue manager
Officiant
Photographer
Caterer lead
Transportation / shuttle
Maid of honor / best person
Parent or family contact 1
Parent or family contact 2
Hotel front desk
NEARBY HELP
Nearest urgent care
Nearest hospital ER
24-hour pharmacy
Tailor or seamstress on call
BACKUP PLAN
Weather backup decision deadline (time)
Who makes the call
Backup ceremony space
Backup plan for guest comfort (heaters, shade, wraps)