## Start Here
Wedding Planning Checklist
A month-by-month planning guide by Butterfly Soiree, San Diego wedding planner
YOUR DETAILS (yellow cells are yours to edit)
Wedding date |  | Enter your date. Due dates fill in on the checklist.
Estimated guest count
Days until wedding
OVERALL PROGRESS
Tasks completed | 0
Total tasks | 103
Percent complete | 0%
High-priority tasks still open | 42
PROGRESS BY TIMEFRAME
Timeframe | Done | Total | % Complete
12+ Months Before | 0 | 13 | 0%
10-11 Months Before | 0 | 8 | 0%
8-9 Months Before | 0 | 8 | 0%
6-7 Months Before | 0 | 8 | 0%
4-5 Months Before | 0 | 8 | 0%
3 Months Before | 0 | 8 | 0%
2 Months Before | 0 | 8 | 0%
1 Month Before | 0 | 9 | 0%
2 Weeks Before | 0 | 7 | 0%
1 Week Before | 0 | 6 | 0%
Day Before | 0 | 5 | 0%
Wedding Day | 0 | 8 | 0%
After the Wedding | 0 | 7 | 0%
HOW TO USE THIS CHECKLIST
1. Enter your wedding date in the yellow cell above. Due dates on the checklist calculate automatically.
2. On the Planning Checklist tab, use the Done dropdown (☐ / ☑) to tick tasks off. Completed rows fade out.
3. Set a Priority and Owner for each task using the dropdowns. Overdue dates turn pink.
4. Use the Budget Tracker for estimates and actual spend, and Vendor Contacts for contracts and payments.
5. Timelines are guidelines. Peak-season dates, destination weddings and larger guest counts usually need more lead time.
Created by Butterfly Soiree ¦ butterflysoiree.com ¦ Full-service, luxury, day-of and destination wedding planning in San Diego

## Planning Checklist
Wedding Planning Checklist
Butterfly Soiree ¦ Enter your wedding date on the Start Here tab and due dates fill in automatically.
Done | Timeframe | Category | Task | Priority | Owner | Due Date | Notes & San Diego Tips | Days before (helper)
12+ MONTHS BEFORE
☐ | 12+ Months Before | Budget | Set your total wedding budget and agree who is contributing | High |  |  | Decide this before touring venues so every quote is measured against a real number. | 365
☐ | 12+ Months Before | Guests | Draft a preliminary guest list (A-list / B-list tiers) | High |  |  | Guest count drives venue size, catering, rentals and cost. | 365
☐ | 12+ Months Before | Vision | Define your wedding vision, style and top 3 priorities | High |  |  | Pick 3 must-haves (e.g. food, photography, music) and spend there first. | 365
☐ | 12+ Months Before | Planning Team | Interview and hire a wedding planner or day-of coordinator | High |  |  | Booking early gives access to vendor referrals and venue insight. | 365
☐ | 12+ Months Before | Date | Choose your season, preferred month and 2-3 flexible dates | High |  |  | Weekday, Friday and Sunday dates can lower venue minimums. | 365
☐ | 12+ Months Before | Venue | Research and tour ceremony and reception venues | High |  |  | Ask about weather backup, noise curfew, load-in times and vendor rules. | 365
☐ | 12+ Months Before | Venue | Review the venue contract, then book and secure your date | High |  |  | Check capacity, overtime fees, insurance requirements and cancellation terms. | 365
☐ | 12+ Months Before | Permits | Confirm permit rules if marrying outdoors or on a beach | Medium |  |  | San Diego beaches and parks have their own permit and capacity rules. Confirm with the managing agency. | 365
☐ | 12+ Months Before | Vendors | Book your photographer | High |  |  | Top photographers book 12+ months out for peak dates. | 365
☐ | 12+ Months Before | Vendors | Book your caterer (if venue does not provide catering) | High |  |  |  | 365
☐ | 12+ Months Before | Vendors | Book entertainment: DJ, band or musicians | Medium |  |  |  | 365
☐ | 12+ Months Before | Vendors | Book videographer (optional) | Low |  |  |  | 365
☐ | 12+ Months Before | Admin | Research wedding insurance and venue liability requirements | Low |  |  | Some venues require a liability certificate from you. | 365
10-11 MONTHS BEFORE
☐ | 10-11 Months Before | Vendors | Book your florist or wedding designer | High |  |  | Share your mood board and budget up front so proposals stay realistic. | 315
☐ | 10-11 Months Before | Vendors | Book your officiant | High |  |  |  | 315
☐ | 10-11 Months Before | Attire | Start shopping for the wedding dress or attire | High |  |  | Allow 6-9 months for ordering and alterations. | 315
☐ | 10-11 Months Before | Wedding Party | Choose your wedding party and ask them to stand with you | Medium |  |  |  | 315
☐ | 10-11 Months Before | Website | Create your wedding website and registry link | Medium |  |  | Include venue address, parking, dress code and accommodation details. | 315
☐ | 10-11 Months Before | Registry | Start your wedding registry | Medium |  |  | Mix price points and include experiences or cash funds. | 315
☐ | 10-11 Months Before | Guests | Reserve hotel room blocks for out-of-town guests | Medium |  |  | Negotiate a group rate and a flexible release date. | 315
☐ | 10-11 Months Before | Photos | Book engagement photo session | Low |  |  | Use it for your website and save-the-dates. | 315
8-9 MONTHS BEFORE
☐ | 8-9 Months Before | Vendors | Book hair and makeup artists | Medium |  |  | Confirm travel fees and the number of people they can serve. | 255
☐ | 8-9 Months Before | Vendors | Book cake or dessert baker | Medium |  |  |  | 255
☐ | 8-9 Months Before | Rentals | Book rentals: tables, chairs, linens, lounge furniture | Medium |  |  | Ask your venue what is included before ordering. | 255
☐ | 8-9 Months Before | Vendors | Book lighting and sound/AV if needed | Medium |  |  | Ceremony and dance floor sound are often overlooked. | 255
☐ | 8-9 Months Before | Transport | Book guest shuttle or wedding-day transportation | Medium |  |  | Useful for venues with limited parking. | 255
☐ | 8-9 Months Before | Honeymoon | Research honeymoon destinations and check passport validity | Low |  |  | Passports often need 6 months of validity. | 255
☐ | 8-9 Months Before | Events | Plan rehearsal dinner venue and welcome events | Low |  |  |  | 255
☐ | 8-9 Months Before | Design | Develop decor concept, color palette and mood board | Medium |  |  | Keep one master document so every vendor works from the same vision. | 255
6-7 MONTHS BEFORE
☐ | 6-7 Months Before | Guests | Send save-the-dates | High |  |  | Send 8-12 months out for destination or holiday weekend weddings. | 195
☐ | 6-7 Months Before | Stationery | Choose and order invitations and stationery suite | High |  |  | Order extras for vendors, photography flat-lays and keepsakes. | 195
☐ | 6-7 Months Before | Attire | Order the wedding dress and bridesmaid attire | High |  |  | Order early. Lead times and alterations take months. | 195
☐ | 6-7 Months Before | Attire | Choose partner and groomsmen attire | Medium |  |  |  | 195
☐ | 6-7 Months Before | Rings | Shop for wedding bands | Medium |  |  | Allow time for sizing and engraving. | 195
☐ | 6-7 Months Before | Catering | Schedule menu tasting and confirm dietary needs | Medium |  |  |  | 195
☐ | 6-7 Months Before | Honeymoon | Book honeymoon flights and accommodations | Low |  |  |  | 195
☐ | 6-7 Months Before | Ceremony | Book ceremony musicians | Low |  |  |  | 195
4-5 MONTHS BEFORE
☐ | 4-5 Months Before | Design | Finalize floral, decor and rentals with your designer | High |  |  | Lock in quantities after the guest count is firm. | 135
☐ | 4-5 Months Before | Menu | Finalize catering menu, bar plan and service style | High |  |  |  | 135
☐ | 4-5 Months Before | Ceremony | Plan the ceremony structure, readings and vows | Medium |  |  | Confirm timing, processional order and any cultural elements. | 135
☐ | 4-5 Months Before | Counseling | Complete any premarital or officiant meetings required | Low |  |  |  | 135
☐ | 4-5 Months Before | Beauty | Book hair and makeup trial | Medium |  |  |  | 135
☐ | 4-5 Months Before | Favors | Order wedding favors and welcome bags | Low |  |  |  | 135
☐ | 4-5 Months Before | Attire | Schedule first dress fitting | Medium |  |  |  | 135
☐ | 4-5 Months Before | Showers | Coordinate engagement party, bridal shower and bachelor/bachelorette plans | Low |  |  | Share your guest list so hosts do not invite overlap. | 135
3 MONTHS BEFORE
☐ | 3 Months Before | Guests | Mail invitations (8-10 weeks before the wedding) | High |  |  | Set an RSVP deadline 3-4 weeks before the wedding. | 90
☐ | 3 Months Before | Legal | Apply for your marriage license | High |  |  | California licenses are valid for 90 days. Confirm current requirements with the San Diego County Clerk. | 90
☐ | 3 Months Before | Timeline | Draft your wedding-day timeline with your planner | High |  |  | Work backwards from ceremony start and sunset. | 90
☐ | 3 Months Before | Music | Share must-play, do-not-play and key moment songs with your DJ/band | Medium |  |  |  | 90
☐ | 3 Months Before | Rings | Confirm ring engraving and delivery | Low |  |  |  | 90
☐ | 3 Months Before | Design | Approve final decor layout and ceremony set-up | Medium |  |  |  | 90
☐ | 3 Months Before | Rentals | Confirm rentals, lounge items and specialty decor | Medium |  |  |  | 90
☐ | 3 Months Before | Registry | Review registry and add items at different price points | Low |  |  |  | 90
2 MONTHS BEFORE
☐ | 2 Months Before | Guests | Track RSVPs and follow up on missing responses | High |  |  |  | 60
☐ | 2 Months Before | Seating | Draft the seating chart and table layout | Medium |  |  | Wait for RSVPs, then adjust. | 60
☐ | 2 Months Before | Photography | Send photographer your family-photo list and must-have shots | High |  |  | Name a family member to help gather groups. | 60
☐ | 2 Months Before | Vendors | Confirm every vendor's arrival time, scope and contact | High |  |  |  | 60
☐ | 2 Months Before | Attire | Attend second dress fitting and confirm all attire | Medium |  |  |  | 60
☐ | 2 Months Before | Vows | Write personal vows (if applicable) | Medium |  |  |  | 60
☐ | 2 Months Before | Beauty | Complete hair and makeup trial | Medium |  |  | Bring inspiration photos and your veil or hair accessories. | 60
☐ | 2 Months Before | Weather | Create a weather plan: marine layer, wind, heat or rain | Medium |  |  | Coastal San Diego mornings and evenings can be cool and breezy, so plan guest comfort. | 60
1 MONTH BEFORE
☐ | 1 Month Before | Guests | Confirm final guest count after RSVP deadline | High |  |  | Provide final numbers to caterer, rentals, bar and stationer. | 30
☐ | 1 Month Before | Seating | Finalize seating chart and place cards | High |  |  |  | 30
☐ | 1 Month Before | Payments | Create a final payment schedule for all vendors | High |  |  | Confirm due dates, tips and any overtime fees. | 30
☐ | 1 Month Before | Timeline | Share final timeline with vendors and wedding party | High |  |  |  | 30
☐ | 1 Month Before | Legal | Pick up marriage license and confirm who will return it after the wedding | High |  |  | Assign the signing/return responsibility to someone reliable. | 30
☐ | 1 Month Before | Attire | Final dress fitting and break in shoes | Medium |  |  |  | 30
☐ | 1 Month Before | Roles | Assign day-of roles: gift table, card box, decor pack-down | Medium |  |  | Your coordinator can manage this so family can relax. | 30
☐ | 1 Month Before | Tips | Prepare vendor tip and payment envelopes | Medium |  |  |  | 30
☐ | 1 Month Before | Transport | Confirm transportation pick-ups and shuttle schedule | Medium |  |  |  | 30
2 WEEKS BEFORE
☐ | 2 Weeks Before | Print | Finalize programs, menus, signage and escort cards | High |  |  | Proof every name and spelling. | 14
☐ | 2 Weeks Before | Catering | Send final headcount and dietary list to caterer | High |  |  |  | 14
☐ | 2 Weeks Before | Attire | Pick up dress and attire | Medium |  |  |  | 14
☐ | 2 Weeks Before | Beauty | Schedule final beauty appointments | Low |  |  |  | 14
☐ | 2 Weeks Before | Honeymoon | Pack for honeymoon and gather travel documents | Low |  |  |  | 14
☐ | 2 Weeks Before | Weather | Check the forecast and finalize your backup plan | Medium |  |  |  | 14
☐ | 2 Weeks Before | Kit | Build an emergency kit: sewing, stain remover, bandages, mints, pain relievers | Low |  |  |  | 14
1 WEEK BEFORE
☐ | 1 Week Before | Vendors | Final confirmation call or email with each vendor | High |  |  |  | 7
☐ | 1 Week Before | Delivery | Pack and label items for venue: signage, favors, guest book, cake knife | High |  |  | Hand off to your coordinator, not a guest. | 7
☐ | 1 Week Before | Beauty | Manicure, pedicure and final beauty appointments | Low |  |  |  | 7
☐ | 1 Week Before | Timeline | Review the detailed day-of timeline with your wedding party | Medium |  |  |  | 7
☐ | 1 Week Before | Payments | Prepare final balance payments | High |  |  |  | 7
☐ | 1 Week Before | Rehearsal | Confirm rehearsal time, location and attendees | Medium |  |  |  | 7
DAY BEFORE
☐ | Day Before | Rehearsal | Attend ceremony rehearsal | High |  |  |  | 1
☐ | Day Before | Rehearsal | Enjoy rehearsal dinner and share toasts or gifts | Medium |  |  |  | 1
☐ | Day Before | Delivery | Deliver decor and personal items to the venue or coordinator | High |  |  |  | 1
☐ | Day Before | Attire | Steam attire and lay out rings, shoes, jewelry and accessories | Medium |  |  |  | 1
☐ | Day Before | Rest | Hydrate, eat well and aim for a full night's sleep | Medium |  |  |  | 1
WEDDING DAY
☐ | Wedding Day | Morning | Eat breakfast and drink water | High |  |  |  | 0
☐ | Wedding Day | Beauty | Hair and makeup start on schedule | High |  |  |  | 0
☐ | Wedding Day | Photos | Give rings, invitation suite and details to the photographer | Medium |  |  |  | 0
☐ | Wedding Day | Legal | Sign marriage license with officiant and witnesses | High |  |  | Give it to the person responsible for returning it. | 0
☐ | Wedding Day | Vendors | Hand vendor payments and tips to your coordinator | Medium |  |  |  | 0
☐ | Wedding Day | Ceremony | Ceremony begins on time | High |  |  |  | 0
☐ | Wedding Day | Reception | Cocktail hour, dinner, toasts, first dance and cake cutting | High |  |  |  | 0
☐ | Wedding Day | Cleanup | Designate someone to collect gifts, cards, attire and personal items | High |  |  |  | 0
AFTER THE WEDDING
☐ | After the Wedding | Legal | Return the signed marriage license and order certified copies | High |  |  | Confirm the return deadline with the County Clerk. | -14
☐ | After the Wedding | Rentals | Return rentals and collect leftover decor and personal items | Medium |  |  |  | -14
☐ | After the Wedding | Thank You | Send thank-you notes (aim within 3 months) | Medium |  |  | Keep a gift log as you open cards. | -14
☐ | After the Wedding | Attire | Clean and preserve dress and attire | Low |  |  |  | -14
☐ | After the Wedding | Name Change | Update name and documents if changing your name | Low |  |  | Social Security, DMV, passport, banks, employer. | -14
☐ | After the Wedding | Reviews | Leave vendor reviews and share photos | Low |  |  |  | -14
☐ | After the Wedding | Photos | Review gallery and order albums or prints | Low |  |  |  | -14

## Budget Tracker
Wedding Budget Tracker
Total wedding budget ($) | 50000 | Example figure of $50,000. Replace with your own total. Suggested % are editable starting points, not benchmarks. Costs vary by venue, season and guest count.
Category | Suggested % | Estimated ($) | Actual ($) | Paid to Date ($) | Balance Due ($) | Notes
Venue & Rentals | 20% | 10000
Catering & Bar | 25% | 12500
Photography & Video | 12% | 6000
Planner / Coordinator | 10% | 5000
Florals & Decor | 10% | 5000
Music & Entertainment | 7% | 3500
Attire & Beauty | 6% | 3000
Stationery & Paper | 2% | 1000
Cake & Desserts | 2% | 1000
Transportation | 2% | 1000
Ceremony (officiant, license) | 1% | 500
Favors, Gifts & Misc. | 1% | 500
Contingency Buffer | 2% | 1000
TOTAL | 100% | 50000 | 0 | 0 | 0
Over / (under) budget

## Vendor Contacts
Vendor Contacts & Contracts
Vendor Type | Company | Contact Name | Phone | Email | Contract Signed | Deposit Paid | Balance Due Date | Notes
Photographer (EXAMPLE) | Sample Studio | Jane Doe | (619) 555-0123 | hello@example.com | Yes | Yes | 2026-12-01 | Example row. Delete or overwrite.
Venue
Wedding Planner / Coordinator
Photographer
Videographer
Caterer
Florist / Designer
DJ / Band
Officiant
Hair & Makeup
Cake / Desserts
Rentals
Lighting / AV
Transportation
Stationery
Hotel Block