## Start Here
Wedding Planning Timeline
An interactive month-by-month planner from Butterfly Soiree. Enter your wedding date and every milestone gets a date, a status and a place on the timeline.
Wedding date (type yours) |  | Planning start date (optional) |  |  | Days to go |  |  | Weeks to go
2027-10-09 |  | 2026-10-04 |  |  | 370 |  |  | 53 |  | 2026-10-04
370
Planning runway |  | Milestones done |  |  | Overdue |  |  | Due in next 30 days |  | 0.86111
12.2 months |  | 0 of 81 |  |  | 0 |  |  | 2
Pace: comfortable. You have a full year or more, so there is room to compare options.
✓ Nothing overdue. You are on track.
Timeline → |  |  | Key Dates → |  |  |  | Monthly Overview →
YOUR NEXT 10 MILESTONES (updates as you tick things off)
Due | Milestone |  |  |  |  | Phase |  | Status | Owner
2026-10-21 | Set your total budget and who is contributing |  |  |  |  | Foundations |  | In progress |  |  | 46316.0001 | 2
2026-10-30 | Draft your guest list (A-list and B-list) |  |  |  |  | Foundations |  | In progress |  |  | 46325.0001 | 3
2026-11-07 | Define your style and top three priorities |  |  |  |  | Foundations |  | Upcoming |  |  | 46333.0001 | 4
2026-11-16 | Choose your season, month and flexible dates |  |  |  |  | Foundations |  | Upcoming |  |  | 46342.0001 | 5
2026-12-12 | Tour and compare venues |  |  |  |  | Foundations |  | Upcoming |  |  | 46368.0001 | 7
2026-12-21 | Hire your wedding planner or day-of coordinator |  |  |  |  | Foundations |  | Upcoming |  |  | 46377.0001 | 6
2026-12-29 | Book your venue and lock the date |  |  |  |  | Foundations |  | Upcoming |  |  | 46385.0001 | 8
2027-01-15 | Book your photographer |  |  |  |  | Foundations |  | Upcoming |  |  | 46402.0002 | 9
2027-01-15 | Book your caterer (if the venue doesn't provide food) |  |  |  |  | Foundations |  | Upcoming |  |  | 46402.0002 | 10
2027-02-02 | Book DJ, band or ceremony musicians |  |  |  |  | Foundations |  | Upcoming |  |  | 46420.0002 | 11
PROGRESS BY PHASE
Phase |  | Done | Total | % complete
Foundations |  | 0 | 12 | 0%
Core Team |  | 0 | 7 | 0%
Details |  | 0 | 8 | 0%
Paper & Attire |  | 0 | 7 | 0%
Finalizing |  | 0 | 7 | 0%
Invitations & Legal |  | 0 | 5 | 0%
Confirmations |  | 0 | 8 | 0%
Lock It Down |  | 0 | 9 | 0%
Final Two Weeks |  | 0 | 8 | 0%
Wedding Weekend |  | 0 | 3 | 0%
After the Wedding |  | 0 | 7 | 0%
HOW TO USE THIS TIMELINE
1. Type your wedding date in the first yellow card. The sample date is only an example. Replace it with yours.
2. Add your planning start date if you're starting late. The timeline compresses to fit. Leave it blank to see the full 14-month plan.
3. Open the Timeline tab. Tick milestones off with the ☐ / ☑ dropdown. The bars on the right turn green when done and pink when overdue.
4. Need a different date? Type your own in the yellow Your date column. That row and the bars update.
5. Key Dates lists the deadlines that trip people up (invitations, RSVPs, headcount, payments). Adjust the number of days in the yellow cells.
6. Monthly Overview shows how many milestones fall in each month so you can see your busiest stretches.
7. The long-range dates stretch or shrink with your planning runway. Final-month tasks stay fixed, because they don't move with time.
Created by Butterfly Soiree ¦ butterflysoiree.com ¦ Full-service, luxury, day-of and destination wedding planning in San Diego, California
Formulas:
Days to go = IF([Wedding date (type yours)]="","Set date",MAX(0,[Wedding date (type yours)]-TODAY()))
Weeks to go = IF([Wedding date (type yours)]="","Set date",ROUNDUP(MAX(0,[Wedding date (type yours)]-TODAY())/7,0))

## Timeline
Wedding Planning Timeline
← Back to Start Here
| Wedding date: | 2027-10-09 |  | Dates are calculated from your wedding date. To change a due date, type your own in the yellow "Your date" column.
| Gantt key: | Planned window | Done | Overdue | This month
Done | Milestone | Phase | Priority | Owner | Start | Due | Your date (optional) | Status | Tips & notes | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01
FOUNDATIONS ¦ 12+ months out
☐ | Set your total budget and who is contributing | Foundations | High |  | 2026-10-04 | 2026-10-21 |  | In progress | Decide this before touring venues so every quote is measured against a real number. | [22 empty] | 420 | 400 | 2026-10-21
☐ | Draft your guest list (A-list and B-list) | Foundations | High |  | 2026-10-04 | 2026-10-30 |  | In progress | Headcount drives venue size, catering and rentals. | [22 empty] | 420 | 390 | 2026-10-30
☐ | Define your style and top three priorities | Foundations | High |  | 2026-10-13 | 2026-11-07 |  | Upcoming | Spend first on your top three. Trim elsewhere. | [22 empty] | 410 | 380 | 2026-11-07
☐ | Choose your season, month and flexible dates | Foundations | High |  | 2026-10-21 | 2026-11-16 |  | Upcoming | Fridays, Sundays and weekdays often cost less than Saturdays. | [22 empty] | 400 | 370 | 2026-11-16
☐ | Hire your wedding planner or day-of coordinator | Foundations | High |  | 2026-10-30 | 2026-12-21 |  | Upcoming | Earlier hires can steer venue and vendor choices. | [22 empty] | 390 | 330 | 2026-12-21
☐ | Tour and compare venues | Foundations | High |  | 2026-11-07 | 2026-12-12 |  | Upcoming | Ask about weather backup, noise curfews, load-in times and vendor rules. | [22 empty] | 380 | 340 | 2026-12-12
☐ | Book your venue and lock the date | Foundations | High |  | 2026-12-03 | 2026-12-29 |  | Upcoming | Read the contract: capacity, overtime fees, insurance, cancellation terms. | [22 empty] | 350 | 320 | 2026-12-29
☐ | Book your photographer | Foundations | High |  | 2026-12-08 | 2027-01-15 |  | Upcoming | Top photographers fill peak dates a year or more ahead. | [22 empty] | 345 | 300 | 2027-01-15
☐ | Book your caterer (if the venue doesn't provide food) | Foundations | High |  | 2026-12-12 | 2027-01-15 |  | Upcoming | [23 empty] | 340 | 300 | 2027-01-15
☐ | Book DJ, band or ceremony musicians | Foundations | Medium |  | 2026-12-21 | 2027-02-02 |  | Upcoming | [23 empty] | 330 | 280 | 2027-02-02
☐ | Confirm permits for outdoor or public-space ceremonies | Foundations | Medium |  | 2026-12-21 | 2027-02-10 |  | Upcoming | Rules vary by city, park and agency. Ask early. | [22 empty] | 330 | 270 | 2027-02-10
☐ | Review wedding insurance and venue liability requirements | Foundations | Low |  | 2026-12-29 | 2027-02-02 |  | Upcoming | Some venues require a liability certificate from you. | [22 empty] | 320 | 280 | 2027-02-02
CORE TEAM ¦ 9-11 months out
☐ | Book your florist or wedding designer | Core Team | High |  | 2027-01-02 | 2027-02-10 |  | Upcoming | Share your budget range in the first email. | [22 empty] | 315 | 270 | 2027-02-10
☐ | Book your officiant | Core Team | High |  | 2027-01-15 | 2027-02-10 |  | Upcoming | [23 empty] | 300 | 270 | 2027-02-10
☐ | Start shopping for the wedding dress or attire | Core Team | High |  | 2027-01-15 | 2027-03-08 |  | Upcoming | Allow 6 to 9 months for ordering and alterations. | [22 empty] | 300 | 240 | 2027-03-08
☐ | Choose your wedding party | Core Team | Medium |  | 2027-01-15 | 2027-02-10 |  | Upcoming | [23 empty] | 300 | 270 | 2027-02-10
☐ | Launch your wedding website and open your registry | Core Team | Medium |  | 2027-01-24 | 2027-03-08 |  | Upcoming | Include venue address, parking, dress code and hotel info. | [22 empty] | 290 | 240 | 2027-03-08
☐ | Reserve a hotel room block for out-of-town guests | Core Team | Medium |  | 2027-01-24 | 2027-02-27 |  | Upcoming | Negotiate a group rate and a flexible release date. | [22 empty] | 290 | 250 | 2027-02-27
☐ | Book engagement photos | Core Team | Low |  | 2027-02-02 | 2027-04-11 |  | Upcoming | Use them for your website and save-the-dates. | [22 empty] | 280 | 200 | 2027-04-11
DETAILS ¦ 6-8 months out
☐ | Book hair and makeup artists | Details | Medium |  | 2027-02-23 | 2027-04-03 |  | Upcoming | Confirm travel fees and how many people they can serve. | [22 empty] | 255 | 210 | 2027-04-03
☐ | Book your cake or dessert baker | Details | Medium |  | 2027-02-23 | 2027-04-03 |  | Upcoming | [23 empty] | 255 | 210 | 2027-04-03
☐ | Book rentals: tables, chairs, linens, lounge pieces | Details | Medium |  | 2027-02-27 | 2027-04-11 |  | Upcoming | Check what the venue already includes. | [22 empty] | 250 | 200 | 2027-04-11
☐ | Book lighting and sound / AV | Details | Medium |  | 2027-02-27 | 2027-04-11 |  | Upcoming | [23 empty] | 250 | 200 | 2027-04-11
☐ | Book guest shuttle or wedding-day transportation | Details | Medium |  | 2027-03-08 | 2027-04-20 |  | Upcoming | [23 empty] | 240 | 190 | 2027-04-20
☐ | Develop your decor concept, palette and mood board | Details | Medium |  | 2027-03-08 | 2027-04-11 |  | Upcoming | One master document keeps every vendor on the same page. | [22 empty] | 240 | 200 | 2027-04-11 00:01
☐ | Plan the rehearsal dinner and welcome events | Details | Low |  | 2027-03-17 | 2027-04-29 |  | Upcoming | [23 empty] | 230 | 180 | 2027-04-29 00:01
☐ | Research honeymoon options and check passport dates | Details | Low |  | 2027-03-17 | 2027-04-20 |  | Upcoming | Many countries require 6 months of passport validity. | [22 empty] | 230 | 190 | 2027-04-20 00:01
PAPER & ATTIRE ¦ 4-6 months out
☐ | Send save-the-dates | Paper & Attire | High |  | 2027-04-11 | 2027-04-29 |  | Upcoming | Send 8 to 12 months out for destination or holiday-weekend weddings. | [22 empty] | 200 | 180 | 2027-04-29 00:01
☐ | Order the wedding dress and bridesmaid attire | Paper & Attire | High |  | 2027-04-03 | 2027-04-29 |  | Upcoming | Lead times plus alterations take months. | [22 empty] | 210 | 180 | 2027-04-29 00:01
☐ | Order invitations and stationery suite | Paper & Attire | High |  | 2027-04-20 | 2027-05-16 |  | Upcoming | Order extras for vendors and photo flat-lays. | [22 empty] | 190 | 160 | 2027-05-16 00:01
☐ | Choose partner and groomsmen attire | Paper & Attire | Medium |  | 2027-04-29 | 2027-05-25 |  | Upcoming | [23 empty] | 180 | 150 | 2027-05-25 00:01
☐ | Shop for wedding bands | Paper & Attire | Medium |  | 2027-05-07 | 2027-06-11 |  | Upcoming | Leave time for sizing and engraving. | [22 empty] | 170 | 130 | 2027-06-11 00:01
☐ | Hold your menu tasting and share dietary needs | Paper & Attire | Medium |  | 2027-05-16 | 2027-06-19 |  | Upcoming | [23 empty] | 160 | 120 | 2027-06-19 00:01
☐ | Book honeymoon flights and stays | Paper & Attire | Low |  | 2027-05-16 | 2027-06-19 |  | Upcoming | [23 empty] | 160 | 120 | 2027-06-19 00:01
FINALIZING ¦ 3-5 months out
☐ | Finalize florals, decor and rentals | Finalizing | High |  | 2027-06-06 | 2027-07-02 |  | Upcoming | Lock quantities after your guest count is firm. | [22 empty] | 135 | 105 | 2027-07-02 00:01
☐ | Finalize menu, bar plan and service style | Finalizing | High |  | 2027-06-11 | 2027-07-07 |  | Upcoming | [23 empty] | 130 | 100 | 2027-07-07 00:01
☐ | Plan ceremony structure, readings and vows | Finalizing | Medium |  | 2027-06-11 | 2027-07-15 |  | Upcoming | [23 empty] | 130 | 90 | 2027-07-15 00:01
☐ | Book hair and makeup trial | Finalizing | Medium |  | 2027-06-19 | 2027-07-15 |  | Upcoming | [23 empty] | 120 | 90 | 2027-07-15 00:01
☐ | Order favors and welcome bags | Finalizing | Low |  | 2027-06-19 | 2027-07-15 |  | Upcoming | [23 empty] | 120 | 90 | 2027-07-15 00:01
☐ | Attend your first dress fitting | Finalizing | Medium |  | 2027-06-19 | 2027-07-15 |  | Upcoming | [23 empty] | 120 | 90 | 2027-07-15 00:01
☐ | Plan showers and bachelor / bachelorette events | Finalizing | Low |  | 2027-06-19 | 2027-08-10 |  | Upcoming | Share your guest list so hosts don't double-invite. | [22 empty] | 120 | 60 | 2027-08-10 00:01
INVITATIONS & LEGAL ¦ 3 months out
☐ | Mail your invitations | Invitations & Legal | High |  | 2027-08-01 | 2027-08-14 |  | Upcoming | Mail 8 to 10 weeks before the wedding. | [22 empty] | 70 | 56 | 2027-08-14 00:01
☐ | Apply for your marriage license | Invitations & Legal | High |  | 2027-07-15 | 2027-08-25 |  | Upcoming | Rules and validity windows vary by state and county. Check yours. | [22 empty] | 90 | 45 | 2027-08-25 00:01
☐ | Draft your day-of timeline | Invitations & Legal | High |  | 2027-07-15 | 2027-08-10 |  | Upcoming | Work backward from ceremony start and sunset. | [22 empty] | 90 | 60 | 2027-08-10 00:01
☐ | Send your music list to the DJ or band | Invitations & Legal | Medium |  | 2027-07-24 | 2027-08-20 |  | Upcoming | Must-plays, do-not-plays and key-moment songs. | [22 empty] | 80 | 50 | 2027-08-20 00:01
☐ | Approve the final decor layout and ceremony setup | Invitations & Legal | Medium |  | 2027-07-28 | 2027-08-20 |  | Upcoming | [23 empty] | 75 | 50 | 2027-08-20 00:01
CONFIRMATIONS ¦ 2 months out
☐ | Track RSVPs and follow up on missing replies | Confirmations | High |  | 2027-08-14 | 2027-09-11 |  | Upcoming | [23 empty] | 56 | 28 | 2027-09-11 00:01
☐ | Complete your hair and makeup trial | Confirmations | Medium |  | 2027-08-10 | 2027-09-04 |  | Upcoming | Bring inspiration photos and accessories. | [22 empty] | 60 | 35 | 2027-09-04 00:01
☐ | Send photographer your family-photo list and shot list | Confirmations | High |  | 2027-08-20 | 2027-09-09 |  | Upcoming | [23 empty] | 50 | 30 | 2027-09-09 00:01
☐ | Reconfirm every vendor's arrival time and scope | Confirmations | High |  | 2027-08-25 | 2027-09-09 |  | Upcoming | [23 empty] | 45 | 30 | 2027-09-09 00:01
☐ | Attend second dress fitting | Confirmations | Medium |  | 2027-08-25 | 2027-09-09 |  | Upcoming | [23 empty] | 45 | 30 | 2027-09-09 00:01
☐ | Draft your seating chart | Confirmations | Medium |  | 2027-08-25 | 2027-09-18 |  | Upcoming | Wait for RSVPs, then adjust. | [22 empty] | 45 | 21 | 2027-09-18 00:01
☐ | Build your weather backup plan | Confirmations | Medium |  | 2027-08-25 | 2027-09-18 |  | Upcoming | Plan for wind, heat, rain or a cool evening, depending on your venue. | [22 empty] | 45 | 21 | 2027-09-18 00:01
☐ | Write your vows | Confirmations | Medium |  | 2027-08-25 | 2027-09-25 |  | Upcoming | [23 empty] | 45 | 14 | 2027-09-25 00:01
LOCK IT DOWN ¦ 1 month out
☐ | Confirm your final guest count | Lock It Down | High |  | 2027-09-09 | 2027-09-18 |  | Upcoming | Share it with the caterer, rentals, bar and stationer. | [22 empty] | 30 | 21 | 2027-09-18 00:01
☐ | Build your final vendor payment schedule | Lock It Down | High |  | 2027-09-09 | 2027-09-18 |  | Upcoming | Include tips and any overtime fees. | [22 empty] | 30 | 21 | 2027-09-18 00:01
☐ | Finalize seating chart and place cards | Lock It Down | High |  | 2027-09-11 | 2027-09-25 |  | Upcoming | [23 empty] | 28 | 14 | 2027-09-25 00:01
☐ | Share the final timeline with vendors and wedding party | Lock It Down | High |  | 2027-09-11 | 2027-09-25 |  | Upcoming | [23 empty] | 28 | 14 | 2027-09-25 00:01
☐ | Pick up your marriage license | Lock It Down | High |  | 2027-09-09 | 2027-10-02 |  | Upcoming | Decide who is responsible for returning it. | [22 empty] | 30 | 7 | 2027-10-02 00:01
☐ | Final dress fitting; break in your shoes | Lock It Down | Medium |  | 2027-09-18 | 2027-09-29 |  | Upcoming | [23 empty] | 21 | 10 | 2027-09-29 00:01
☐ | Assign day-of roles (gift table, card box, decor pack-down) | Lock It Down | Medium |  | 2027-09-18 | 2027-09-29 |  | Upcoming | [23 empty] | 21 | 10 | 2027-09-29 00:01
☐ | Prepare vendor tip and payment envelopes | Lock It Down | Medium |  | 2027-09-25 | 2027-10-02 |  | Upcoming | [23 empty] | 14 | 7 | 2027-10-02 00:01
☐ | Confirm transportation pick-up times | Lock It Down | Medium |  | 2027-09-25 | 2027-10-02 |  | Upcoming | [23 empty] | 14 | 7 | 2027-10-02 00:01
FINAL TWO WEEKS ¦ 14 days out
☐ | Finalize programs, menus and signage; proofread names | Final Two Weeks | High |  | 2027-09-25 | 2027-09-29 |  | Upcoming | [23 empty] | 14 | 10 | 2027-09-29 00:01
☐ | Send final headcount and dietary list to the caterer | Final Two Weeks | High |  | 2027-09-25 | 2027-09-29 |  | Upcoming | Check your contract for the exact deadline. | [22 empty] | 14 | 10 | 2027-09-29 00:01
☐ | Pick up the dress and attire | Final Two Weeks | High |  | 2027-09-29 | 2027-10-04 |  | Upcoming | [23 empty] | 10 | 5 | 2027-10-04 00:01
☐ | Check the forecast and finalize your backup plan | Final Two Weeks | Medium |  | 2027-09-29 | 2027-10-06 |  | Upcoming | [23 empty] | 10 | 3 | 2027-10-06 00:01
☐ | Pack and label items for the venue; hand off to your coordinator | Final Two Weeks | High |  | 2027-10-02 | 2027-10-07 |  | Upcoming | [23 empty] | 7 | 2 | 2027-10-07 00:01
☐ | Final confirmation with every vendor | Final Two Weeks | High |  | 2027-10-02 | 2027-10-06 |  | Upcoming | [23 empty] | 7 | 3 | 2027-10-06 00:01
☐ | Prepare final balance payments | Final Two Weeks | High |  | 2027-10-02 | 2027-10-06 |  | Upcoming | [23 empty] | 7 | 3 | 2027-10-06 00:01
☐ | Pack for the honeymoon | Final Two Weeks | Low |  | 2027-09-29 | 2027-10-07 |  | Upcoming | [23 empty] | 10 | 2 | 2027-10-07 00:01
WEDDING WEEKEND ¦ Rehearsal and the big day
☐ | Rehearsal and rehearsal dinner | Wedding Weekend | High |  | 2027-10-08 | 2027-10-08 |  | Upcoming | [23 empty] | 1 | 1 | 2027-10-08 00:01
☐ | Deliver decor and personal items to the venue | Wedding Weekend | High |  | 2027-10-08 | 2027-10-08 |  | Upcoming | [23 empty] | 1 | 1 | 2027-10-08 00:01
☐ | Wedding day | Wedding Weekend | High |  | 2027-10-09 | 2027-10-09 |  | Upcoming | Eat breakfast. Hand vendor payments and tips to your coordinator. | [22 empty] | 0 | 0 | 2027-10-09 00:01
AFTER THE WEDDING ¦ Wrap-up
☐ | Return the signed marriage license; order certified copies | After the Wedding | High |  | 2027-10-09 | 2027-10-23 |  | Upcoming | Confirm the return deadline with your county office. | [22 empty] | 0 | -14 | 2027-10-23 00:01
☐ | Return rentals and collect leftover decor | After the Wedding | Medium |  | 2027-10-09 | 2027-10-11 |  | Upcoming | [23 empty] | 0 | -2 | 2027-10-11 00:01
☐ | Send thank-you notes | After the Wedding | Medium |  | 2027-10-16 | 2028-01-07 |  | Upcoming | Keep a gift log as you open cards. | [22 empty] | -7 | -90 | 2028-01-07 00:01
☐ | Clean and preserve the dress and attire | After the Wedding | Low |  | 2027-10-16 | 2027-11-08 |  | Upcoming | [23 empty] | -7 | -30 | 2027-11-08 00:01
☐ | Update your name and documents (if changing it) | After the Wedding | Low |  | 2027-10-23 | 2027-12-08 |  | Upcoming | Social Security, DMV, passport, banks, employer. | [22 empty] | -14 | -60 | 2027-12-08 00:01
☐ | Leave vendor reviews and share photos | After the Wedding | Low |  | 2027-10-23 | 2027-11-23 |  | Upcoming | [23 empty] | -14 | -45 | 2027-11-23 00:01
☐ | Review your gallery and order albums or prints | After the Wedding | Low |  | 2027-11-08 | 2028-01-07 |  | Upcoming | [23 empty] | -30 | -90 | 2028-01-07 00:01

## Key Dates
Key Dates
← Back to Start Here
Deadlines that sneak up on couples. Change the yellow number of days to fit your plan. Dates calculate from your wedding date.
Deadline | Days before wedding | Date | Day | Days away | Status | Rule of thumb
Send save-the-dates | 180 | 2027-04-12 | Monday | 190 | Upcoming | Typically 6 to 8 months out. Send 8 to 12 months out for destination or holiday-weekend weddings.
Hotel room block cutoff | 45 | 2027-08-25 | Wednesday | 325 | Upcoming | Set by the hotel, often 30 to 60 days out. Confirm in your contract.
Marriage license window opens | 90 | 2027-07-11 | Sunday | 280 | Upcoming | Validity and rules vary by state and county. In California, a license is valid for 90 days. Check yours.
Mail invitations | 63 | 2027-08-07 | Saturday | 307 | Upcoming | Usually 8 to 10 weeks before the wedding.
Hair and makeup trial | 60 | 2027-08-10 | Tuesday | 310 | Upcoming | One to two months out, so there's time to adjust.
RSVP deadline | 28 | 2027-09-11 | Saturday | 342 | Upcoming | Three to four weeks out. Ask guests to reply about a week before your caterer's deadline.
Send final timeline to vendors | 14 | 2027-09-25 | Saturday | 356 | Upcoming | Two weeks out gives vendors time to ask questions.
Final headcount to caterer | 14 | 2027-09-25 | Saturday | 356 | Upcoming | Check your catering contract. Many require numbers 7 to 14 days out.
Seating chart finished | 14 | 2027-09-25 | Saturday | 356 | Upcoming | Wait until RSVPs are final.
Final dress fitting | 14 | 2027-09-25 | Saturday | 356 | Upcoming | Usually one to two weeks before.
Final vendor payments due | 7 | 2027-10-02 | Saturday | 363 | Upcoming | Per each contract. Many are due one to two weeks before.
Rehearsal and rehearsal dinner | 1 | 2027-10-08 | Friday | 369 | Upcoming | The day before the wedding.
Wedding day | 0 | 2027-10-09 | Saturday | 370 | Upcoming
Return marriage license / send thank-you notes | -30 | 2027-11-08 | Monday | 400 | Upcoming | Confirm the license return deadline with your county office. Aim for thank-you notes within three months.
Formulas:
Date = IF('Start Here'!$B6="","",'Start Here'!$B6-[Days before wedding])
Days away = IF([Date]="","",[Date]-TODAY())

## Monthly Overview
Monthly Overview
← Back to Start Here
Month | Time to wedding | Milestones due | Completed | Remaining | % done | Typical focus | Your notes
2026-10-01 | 12 months out | 2 | 0 | 2 | 0% | Budget, guest list, venue, planner, photographer
2026-11-01 | 11 months out | 2 | 0 | 2 | 0% | Florist/designer, officiant, attire search, website
2026-12-01 | 10 months out | 3 | 0 | 3 | 0% | Florist/designer, officiant, attire search, website
2027-01-01 | 9 months out | 2 | 0 | 2 | 0% | Florist/designer, officiant, attire search, website
2027-02-01 | 8 months out | 7 | 0 | 7 | 0% | Supporting vendors, decor concept, honeymoon
2027-03-01 | 7 months out | 2 | 0 | 2 | 0% | Supporting vendors, decor concept, honeymoon
2027-04-01 | 6 months out | 11 | 0 | 11 | 0% | Supporting vendors, decor concept, honeymoon
2027-05-01 | 5 months out | 2 | 0 | 2 | 0% | Save-the-dates, invitations, dress, tasting
2027-06-01 | 4 months out | 3 | 0 | 3 | 0% | Save-the-dates, invitations, dress, tasting
2027-07-01 | 3 months out | 6 | 0 | 6 | 0% | Finalize design and menu, fittings
2027-08-01 | 2 months out | 6 | 0 | 6 | 0% | Invitations out, license, timeline
2027-09-01 | 1 months out | 16 | 0 | 16 | 0% | RSVPs, confirmations, seating
2027-10-01 | Wedding month | 14 | 0 | 14 | 0% | Final details, rehearsal, wedding day
2027-11-01 | 1 mo. after | 2 | 0 | 2 | 0% | Wrap-up, thank-yous, paperwork
2027-12-01 | 2 mo. after | 1 | 0 | 1 | 0% | Wrap-up, thank-yous, paperwork
2028-01-01 | 3 mo. after | 2 | 0 | 2 | 0% | Wrap-up, thank-yous, paperwork
2028-02-01 | 4 mo. after | 0 | 0 | 0 |  | Wrap-up, thank-yous, paperwork
2028-03-01 | 5 mo. after | 0 | 0 | 0 |  | Wrap-up, thank-yous, paperwork
2028-04-01 | 6 mo. after | 0 | 0 | 0 |  | Wrap-up, thank-yous, paperwork
2028-05-01 | 7 mo. after | 0 | 0 | 0 |  | Wrap-up, thank-yous, paperwork
2028-06-01 | 8 mo. after | 0 | 0 | 0 |  | Wrap-up, thank-yous, paperwork
2028-07-01 | 9 mo. after | 0 | 0 | 0 |  | Wrap-up, thank-yous, paperwork
Peach row = this month. Pink row = your wedding month. Bars show the share of that month's milestones you've completed.
Formulas:
Milestones due = IF([Month]="","",COUNTIFS(Timeline!$G8:G99,">="&[Month],Timeline!$G8:G99,"<="&EOMONTH([Month],0)))
Completed = IF([Month]="","",COUNTIFS(Timeline!$G8:G99,">="&[Month],Timeline!$G8:G99,"<="&EOMONTH([Month],0),Timeline!$A8:A99,"☑"))